## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
USER STORY | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Spike: Jsp | 5 | Oskar, Yousaf | Completed | 5 | 2 | 1 | 0 | 0 | 0 | 0
Spike: Python Backend | 5 | Blazej | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0
Spike: Integration with JSP | 5 | Oskar, Yousaf, Blazej and Roman | Completed | 5 | 5 | 4 | 0 | 0 | 0 | 0
As a user, I want to use my current location, to help me locate the nearest institution. | 5 | Blazej | In Progress | 5 | 5 | 4 | 4 | 2 | 2 | 2
Design front-end | 1 | Gregor and Sarah | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0
Back-end implementation | 3 | Oskar, Yousaf, Blazej and Roman | In Progress | 3 | 3 | 3 | 3 | 2 | 2 | 2
Integration with Front-end | 1 | Oskar and Yousaf | Completed | 1 | 1 | 1 | 1 | 0 | 0 | 0
As a user, I want to filter my search by price and distance to find my optimal care. | 6 | Yousaf |  | 6 | 6 | 5 | 4 | 4 | 2 | 2
Front-end implementation | 2 | Gregor and Sarah | Completed | 2 | 2 | 1 | 0 | 0 | 0 | 0
Back-end implementation | 3 | Oskar, Yousaf, Blazej and Roman | In Progress | 3 | 3 | 3 | 3 | 3 | 2 | 2
Integration with Front-end | 1 | Oskar and Yousaf | Completed | 1 | 1 | 1 | 1 | 1 | 0 | 0
As a user I want to view the search results on a map, so that I can make a choice based on their location. | 5 | Blazej |  | 5 | 5 | 5 | 5 | 3 | 0 | 0
Back-end implementation | 3 | Oskar, Yousaf, Blazej and Roman | Completed | 3 | 3 | 3 | 3 | 2 | 0 | 0
Integration with Front-end | 2 | Blazej | Completed | 2 | 2 | 2 | 2 | 1 | 0 | 0
As a user, I want to be able to see the price information for each result on the map, to help me make a decision on a medical institution | 6 | Sarah |  | 6 | 5 | 5 | 4 | 4 | 4 | 4
Front-end implementation | 1 | Gregor and Sarah | Completed | 1 | 1 | 1 | 0 | 0 | 0 | 0
Back-end implementation | 3 | Oskar, Yousaf, Blazej and Roman | Not Started | 3 | 3 | 3 | 3 | 3 | 3 | 3
Integration with Front-end | 1 | Oskar and Yousaf | Not Started | 1 | 1 | 1 | 1 | 1 | 1 | 1
As a user, I want to view the search results as a list, so I can compare my options | 5 | Sarah |  | 5 | 5 | 5 | 4 | 3 | 0 | 0
Front-end implementation | 1 | Gregor and Sarah | Completed | 1 | 1 | 1 | 0 | 0 | 0 | 0
Back-end implementation | 3 | Oskar, Yousaf, Blazej and Roman | Completed | 3 | 3 | 3 | 3 | 2 | 0 | 0
Integration with Front-end | 1 | Oskar and Yousaf | Completed | 1 | 1 | 1 | 1 | 1 | 0 | 0
As a user, I want to search by price, to find an affordable cost for a procedure | 6 | Gregor |  | 6 | 6 | 5 | 4 | 4 | 3 | 3
Front-end implementation | 2 | Gregor and Sarah | Completed | 2 | 2 | 1 | 0 | 0 | 0 | 0
Back-end implementation | 3 | Oskar, Yousaf, Blazej and Roman | In Progress | 3 | 3 | 3 | 3 | 3 | 1 | 1
Integration with Front-end | 1 | Oskar and Yousaf | Not Started | 1 | 1 | 1 | 1 | 1 | 1 | 1
As a user I want to search by location, to help me locate nearby institutions | 4 | Oskar |  | 4 | 4 | 4 | 4 | 4 | 3 | 3
Back-end implementation | 3 | Oskar, Yousaf, Blazej and Roman | In Progress | 3 | 3 | 3 | 3 | 3 | 1 | 1
Integration with Front-end | 1 | Oskar and Yousaf | Not Started | 1 | 1 | 1 | 1 | 1 | 1 | 1
As a user, I want to order the search results by distance, to help me identify the nearest institution for my treatment | 4 | Blazej |  | 4 | 4 | 4 | 4 | 4 | 0 | 0
Back-end implementation | 3 | Oskar, Yousaf, Blazej and Roman | Completed | 3 | 3 | 3 | 3 | 3 | 0 | 0
Integration with Front-end | 1 | Oskar and Yousaf | Completed | 1 | 1 | 1 | 1 | 1 | 0 | 0
As a user, I want to be able to search for a procedure by it's description so that I can be treated | 4 | Roman |  | 4 | 4 | 4 | 4 | 3 | 2 | 2
Back-end implementation | 3 | Oskar, Yousaf, Blazej and Roman | In Progress | 3 | 3 | 3 | 3 | 2 | 2 | 2
Integration with Front-end | 1 | Oskar and Yousaf | Completed | 1 | 1 | 1 | 1 | 1 | 0 | 0
As a user, I want to order by price, to find the most affordable care in my area | 4 | Oskar |  | 4 | 4 | 4 | 4 | 2 | 0 | 0
Back-end implementation | 3 | Oskar, Yousaf, Blazej and Roman | Completed | 3 | 3 | 3 | 3 | 2 | 0 | 0
Integration with Front-end | 1 | Oskar and Yousaf | Completed | 1 | 1 | 1 | 1 | 0 | 0 | 0
As a user, I want to search for a procedure by its code so i can be treated | 4 | Oskar |  | 4 | 4 | 4 | 3 | 1.5 | 1 | 1
Back-end implementation | 3 | Oskar, Yousaf, Blazej and Roman | In Progress | 3 | 3 | 3 | 2 | 1 | 1 | 1
Integration with Front-end | 1 | Oskar and Yousaf | Completed | 1 | 1 | 1 | 1 | 0.5 | 0 | 0
TOTAL | 68 |  |  | 68 | 63 | 53 | 44 | 34.5 | 17 | 17