## Sheet1
BACKLOG TASK | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Spike: Google Maps API | 7 | Blazej | Completed | 100% | 0%
Read Google Maps API doc |  | Blazej | Completed | 100% | 0%
Practice using the API |  | Blazej | Completed | 100% | 0%
Spike: Azure SQL DB Hosting | 6 | Roman | In Progress | 100% | 80%
Investigate hosting an SQL database on Azure |  | Roman | In Progress | 100% | 80%
Spike: Host Java web app on Azure | 8 | Oskar | In Progress | 100% | 90%
Investigate hosting a web app on azure |  | Oskar, Yousaf | In Progress | 100% | 80%
Inevstigate continuous deployment |  | Yousaf, Oskar | Not Started | 100% | 100%
Spike: Investigate spring framework | 5 | Yousaf | In Progress | 100% | 75%
Investigate Spring framework |  | Yousaf | In Progress | 100% | 50%
Create a Spring application |  | Yousaf | Not Started | 100% | 100%
As a user, I want to be able to see the price information for each result on the map, to help me make a decision on a medical institution | 8 | Sarah | In Progress | 100% | 56%
Design front-end view for this |  | Sarah, Gregor | In Progress | 100% | 40%
back-end implementation and integration with the front end |  | Sarah, Blazej | Not Started | 100% | 100%
Use custom markers on the map |  | Blazej | In Progress | 100% | 30%
As a user, I want to view the search results as a list, so I can compare my options | 2 | Sarah | In Progress | 100% | 90%
Design front-end view for this |  | Sarah | In Progress | 100% | 80%
back-end implementation and integration with the front end |  | Sarah, Blazej | Not Started | 100% | 100%
As a user, I want to search by price, to find an affordable cost for a procedure | 4 | Gregor | In Progress | 100% | 65%
Design front-end view for this |  | Sarah, Gregor | In Progress | 100% | 30%
back-end implementation and integration with the front end |  | Yousaf | Not Started | 100% | 100%
As a user I want to search by location, to help me locate nearby institutions | 7 | Blazej | In Progress | 100%
Design front-end view for this |  | Sarah, Gregor | In Progress | 100% | 30%
back-end implementation and integration with the front end |  | Blazej | Not Started | 100% | 100%
Use geocoding API to mark institutions on the map |  | Blazej | Completed | 100% | 0%
As a user, I want to order the search results by distance, to help me identify the nearest institute | 7 | Blazej | In Progress | 100% | 40%
Design front-end view for this |  | Sarah, Gregor | In Progress | 100% | 20%
back-end implementation and integration with the front end |  | Oskar | Not Started | 100% | 100%
Calculate the distance using Distance Matrix API |  | Blazej | Completed | 100% | 0%
As a user, I want to be able to search for a procedure by it's description so that I can be treated | 7 | Roman | In Progress | 100% | 40%
Design front-end view for this |  | Sarah, Gregor | In Progress | 100% | 30%
back-end implementation and integration with the front end |  | Oskar, Blazej, Roman | In Progress | 100% | 50%
As a user, I want to order by price, to find the most affordable care in my area | 1 | Oskar | In Progress | 100% | 60%
Design front-end view for this |  | Sarah, Gregor | In Progress | 100% | 20%
back-end implementation and integration with the front end |  | Oskar | Not Started | 100% | 100%
USER STORY #1