## Agile Product Backlog
USER STORY | SPRINT # | ASSIGNED TO | START | FINISH | PRIORITY | COMPLEXITY | STATUS | RETURN ON INVESTMENT
Sprint 1
As a developer I want to learn about Spring Framework for Java, in order to see if it is worth using. | 1 | Yousaf | 27/01/2020 | 28/01/2020 | 5 | 5 | Complete | 1
As a developer I want to learn how to use java with an SQL database, so that we can pull data from the database efficiently. | 1 | Roman | 27/01/2020 | 29/01/2020 | 8 | 8 | Complete | 1
As a developer, I want to learn how to host a java web app on microsoft azure and leverage the robustness of azure hosting to provide reliable service to the user. | 1 | Oskar | 27/01/2020 | 2020-01-17 | 8 | 8 | Complete | 1
As a developer, I want to learn about Google Maps API, so that we can utilise it and deliver a better quality service. | 1 | Blazej | 27/01/2020 | 27/01/2020 | 7 | 7 | Complete | 1
As a developer, I want to learn how to host an SQL database on an Azure service to provide a way for developers to access data. | 1 | Roman | 28/01/2020 | 29/01/2020 | 8 | 8 | Complete | 1
As a user, I want to search by price, to find affordable cost for a procedure. | 1 | Gregor | 27/01/2020 | Moved to sprint 2 | 8 | 4 | In Progress | 2
As a user, I want to search by location, to help me locate nearby instutions for my treatment. | 1 | Blazej | 27/01/2020 | Moved to sprint 2 | 8 | 7 | In Progress | 1
As a user, I want to be able to search for a procedure by its description so that I can be treated. | 1 | Roman | 27/01/2020 | Moved to sprint 2 | 7 | 7 | In Progress | 1
As a user, I want to be able to search for a procedure by its code so that I can be treated. | 1 | Roman | 27/01/2020 | Moved to sprint 2 | 5 | 3 | In Progress | 1.5
As a user, I want to order by price, to find the most affordable care in my area. | 1 | Oskar | 27/01/2020 | Moved to sprint 2 | 7 | 1 | In Progress | 7
As a user, I want to order the search results by distance to help me identify the nearest institution for treatment. | 1 | Blazej | 27/01/2020 | Moved to sprint 2 | 7 | 7 | In Progress | 1
As a user, I want to view the search results as a list, so I can compare my options | 1 | Sarah | 27/01/2020 | Moved to sprint 2 | 8 | 2 | In Progress | 4
As a user, I want to be able to see the price information for each result on the map, to help me make a decision | 1 | Sarah | 27/01/2020 | Moved to sprint 2 | 3 | 8 | In Progress | 0.5
Sprint 2
As a user, I want to view the search results as a list, so I can compare my options | 1 | Sarah | 2020-01-03 |  | 8 | 2 | In Progress | 4
As a user, I want to use my current location, to help me locate the nearest institution. | 2 | Blazej | 2020-01-03 |  | 4 | 5 | In Progress | 0.5
As a user, I want to search by location, to help me locate nearby instutions for my treatment. | 1 | Blazej | 2020-01-03 |  | 8 | 4 | In Progress | 2
As a user, I want to be able to search for a procedure by its code so that I can be treated. | 1 | Roman | 2020-01-03 |  | 5 | 4 | In Progress | 1.5
As a user, I want to be able to search for a procedure by its description so that I can be treated. | 1 | Roman | 2020-01-03 |  | 7 | 4 | In Progress | 2
As a user, I want to search by price, to find affordable cost for a procedure. | 1 | Gregor | 2020-01-03 |  | 8 | 6 | In Progress | 1.5
As a user, I want to filter my search based on price and distance, to find my optimal care. | 2 | Yousaf | 2020-01-03 |  | 4 | 6 | In Progress | 0.5
As a user, I want to order by price, to find the most affordable care in my area. | 1 | Oskar | 2020-01-03 |  | 7 | 1 | In Progress | 7
As a user, I want to order the search results by distance to help me identify the nearest institution for treatment. | 1 | Blazej | 2020-01-03 |  | 7 | 4 | In Progress | 2
As a user I want to view the search results on a map, so that I can make a choice based on their location. | 2 | Blazej | 2020-01-03 |  | 4 | 5 | In Progress | 0.5
As a user, I want to be able to see the price information for each result on the map, to help me make a decision | 1 | Sarah | 2020-01-03 |  | 3 | 6 | In Progress | 0.5